# Project Charter

## Health Promoting Mall Readiness Assessment & Decision Support Platform

### Executive Summary

As part of HPB's Health Promoting Town (HPT) initiative, this project aims to develop a comprehensive understanding of Singapore’s shopping mall landscape and identify and prioritise shopping malls across Singapore that have the highest potential to serve as Health Promoting Malls (HPMs).

Building on the existing HPM framework, which encompasses domains in nutrition, physical activity, healthy living infrastructures and landlord support on health initiatives, the project will conduct a nationwide audit of shopping malls. It will examine the extent to which malls already embody HPM criteria, including whether existing HPMs demonstrate stronger health-promoting attributes than non-HPMs.

Using these insights, the project will develop an objective, data-driven evaluation framework to benchmark every mall against HPB's HPM criteria and quantify readiness gaps. The analysis will also explore differences across mall chains and independent malls, highlighting which landlords or portfolios are already well-positioned and which require greater engagement or capability building.

Building on the existing HPT concept that defines Health Promoting Malls through nutrition, fitness, healthy living infrastructure, health services and landlord support, this project will create an objective, data-driven framework to assess malls nationwide and identify a pioneer group of malls suitable for future health promotion partnerships and interventions.

The project will culminate in an interactive dashboard or web-based decision support platform that enables decision makers to dynamically adjust evaluation criteria and shortlist malls based on configurable readiness thresholds, allowing HPB to tailor engagement strategies and identify opportunities to capitalise on HPMs strengths and contribute to the overall HPT initiative.

# Problem Statement

Existing evaluation of potential Health Promoting Malls is largely qualitative and manually conducted.

Comparing malls solely using absolute counts of amenities introduces biases:

- Large malls naturally contain more tenants

- Large malls naturally host more activities

- Small but highly health-focused malls may be overlooked

A standardised and normalised evaluation framework is required to:

- Compare malls fairly across important health promoting factors (such as healthier dining options)

- Integrate these into consolidated index (preliminary called HPB Index) to enable decision making across multiple health promoting factors

- Support transparent decision making

- Enable repeatable nationwide assessment

# Project Objectives

### Primary Objective

Develop a Health Promoting Mall Readiness Index ("HPM Index") to fairly evaluate and rank shopping malls in Singapore across an agreed list of health promoting factors.

Support CIP team in identifying and prioritising key malls to target for onboarding to HPM based on surrounding population information which is indicative of potential “reach” and “impact”.

### Secondary Objectives

- Consolidate mall amenity information into a common repository. This may include culling information from publicly available sources.

- Consolidate and clean a defined list of health promoting factors into a common repository.

- Develop normalised mall readiness scores to compare the coverage of facilities by the % rather than absolute count to be a fair assessment among malls in different sizes.

- Integrate demand-side indicators.

- Visualise mall performance geographically.

- Enable interactive scenario planning and weight adjustment.

- Produce a shortlist of candidate malls for HPB engagement.

- Identify regions that should be priortisied for HPM expansion based on lack of existing HPM coverage around the region or demographic/population needs

# Key Milestones and Work Stream

| Key Milestones | Primary Deliverable | Supporting Outputs | Roles |
| --- | --- | --- | --- |
| Milestone 1 | A set of normalised scores according to the list of health promoting factors | Consolidate mall amenity information into a common repository. This may include culling information from publicly available sources Consolidate and clean a defined list of health promoting factors into a common repository | CIP to supply the list of health promoting factors and all the necessary data points available CDOO to review and augment the data points as needed. CDOO to build deliverable |
| Milestone 2 | Layer on potential HPM impact parameters (such residential population around the mall) | Consolidate and clean a defined list of potential impact parameters | CIP and CDOO discuss and agree on the proposed impact parameters CDOO to build deliverable |
| Milestone 3 | Create a composite HPM index by integrating the list of health promoting factors and weights |  | CIP to comment on integration framework and weights CDOO to build deliverable |

# Key Design Principle

## Normalised Assessment Instead of Raw Counts (Milestone 1)

The evaluation will not simply count facilities.

Example:

| Mall | Healthy Dining Stores | Total F&B Stores |
| --- | --- | --- |
| Mall A | 20 | 100 |
| Mall B | 8 | 20 |

Raw count ranking:

- Mall A = 20

- Mall B = 8

Normalised ranking:

- Mall A = 20%

- Mall B = 40%

Mall B may actually be more aligned with health promotion objectives.

This principle will apply across all dimensions.

# Proposed Readiness Framework

## Category A – Healthy Dining Ecosystem

Measures:

- Number of HDP outlets

- % of F&B outlets participating in HDP

- % of healthy-oriented food options

- Presence of supermarket with healthier choice options

Illustrative Weight: 25%

## Category B – Physical Activity Ecosystem

Measures:

- Gyms

- Fitness studios

- Tenants promoting physical activity (e.g. Decathlon, Skechers, Bicycle shops)

- Sports facilities

- Wellness facilities

- Mall-hosted exercise programmes or HPB workouts

Normalised Metrics:

- Fitness facilities per 100 tenants

- Fitness floor area proportion

Illustrative Weight: 20%

## Category C – H365 & HPB Engagement

Measures:

- H365 event locations

- HPB programme locations

- Community activation points

- Historical event frequency

Normalised Metrics:

- Events per month

- Events per 10,000 visitors

Illustrative Weight: 15%

## Category D – Healthcare ecosystem

Measures:

- Clinics

- Pharmacies

- Healthier SG providers

- Health services availability

Illustrative Weight: 10%

## Category E – Healthy Infrastructure

Measures:

- Bicycle parking

- Water refill points

- Community spaces

- Walking-friendly design

- Green spaces

- Children’s playground

- Sports facilities (e.g. fitness corners)

- Wellness facilities (e.g. quiet corners/calm rooms)

Illustrative Weight: 10%

## Category F – Landlord & Partnership Readiness

Measures:

- Previous HPB partnerships

- Health promotion campaigns

- Event collaboration history

- Willingness to participate

Illustrative Weight: 10%

## Category G – Demand Potential

This captures opportunity instead of supply.

Illustrative Weight: 10%

# Demand-Side Metrics (Milestone 2)

Rather than only evaluating what exists today, the framework should identify where HPB interventions may create the highest impact.

Potential indicators:

### Existing Health Demand

- H365 participation near mall

- HPB programme attendance

- Event registration rates

### Untapped Demand

- Low H365 participation despite high footfall

- Low healthy dining exposure

- Under-served health promotion locations

### Population Reach

- Nearby residential population

- Catchment population

- Worker population

- Senior population

### Accessibility

- MRT connectivity

- Bus connectivity

# Composite Health Promoting Mall Index

Proposed approach:

1 Health Promoting Mall Index 2 3 = 4 Supply Readiness Score (70%) 5 + 6 Demand Opportunity Score (30%)

Where:

1 Supply Readiness 2 = 3 Dining 4 + 5 Fitness 6 + 7 Healthcare 8 + 9 Infrastructure 10 + 11 Partnership Readiness 12 + 13 H365 Presence

1 Demand Opportunity 2 = 3 Reach 4 + 5 Population 6 + 7 Accessibility 8 + 9 Engagement Gap

# Interactive Dashboard Features

## Page 1 – Executive Summary

Display:

- Total malls assessed

- Average readiness score

- Top 10 malls

- Top landlords

## Page 2 – National Ranking

Dynamic mall ranking table:

| Rank | Mall | Score | Tier |
| --- | --- | --- | --- |

Filters:

- Region

- Mall operator

- Health readiness level

## Page 3 – What-If Simulator

Users can adjust sliders:

- Dining Weight

- Fitness Weight

- H365 Weight

- Demand Weight

- Accessibility Weight

Ranking updates instantly.

This would likely be one of the most valuable capabilities for management discussions.

## Page 4 – Mall Comparison

Compare:

- Up to 5 malls

- Radar chart

- Strengths and weaknesses

## Page 5 – National Map

Interactive map showing:

- Mall locations

- Score colouring

- Candidate shortlist

This aligns well with the broader HPT geospatial dashboard vision and use cases around interactive maps, wayfinding and amenity analysis.

# Recommended POC Success Criteria

The POC is considered successful if it can:

✅ Assess at least the major shopping malls in Singapore

✅ Produce a repeatable Health Promoting Mall Index

✅ Allow users to change weights dynamically

✅ Instantly generate a different shortlist

✅ Identify Top 10, Top 20 and Top 50 candidate malls

# Potential Enhancement

Rather than only giving a Readiness Score, create a 2x2 Strategic Matrix:

|  | High Demand | Low Demand |
| --- | --- | --- |
| High Readiness | Pioneer HPM | Quick Wins |
| Low Readiness | Strategic Investment | Future Monitoring |

This will be far more useful to senior management than a simple ranked list because it explicitly highlights:

- Pioneer HPMs → ready for immediate deployment

- Quick Wins → low effort expansion

- Strategic Investment Targets → high impact opportunities

- Future Monitoring Locations → not immediate priorities

For HPB leadership discussions, this strategic matrix will likely resonate more strongly than a straightforward Top-20 ranking alone.